Steuben County

Task Force on Underage Drinking

Meeting Minutes

July 10, 2019

12:00 – 1:00 pm

7007 Rumsey Street, Bath, NY

| Invited Attendees: Tanya DeNae Harmony Ayers-Friedlander X Jim Bassage Pam Aini Dean Swam | Edna Kayes X Colleen Banik Jerry Bennett X Susan Hooker Krystle Blencowe Betsy Hull | Kyle King Doug Jones Kevin Grover Lorelei Wagner Bill Caudill | Mark Recktenwald Hillary Anderson Kevin Costello Jesse Dow Amanda Wiley |
| --- | --- | --- | --- |
| Introductions |
| Jim Bassage opened the meeting with no introductions needed. No additions or corrections to the minutes were noted. |
| MOUs |
| No discussion took place. |
| Task Force Membership |
| Jim Bassage reminded everyone that we continually need to recruit new members for the UAD Task Force. |
| Recognition |
| Jim Bassage reminded everyone that we continually need discussion of nominees for recognition of coalition members, community members and/or people you know in our area who are doing great things involving our youth and our mission. Colleen Banik indicated that Dean Swan, Pam Aini and Doug Jones need significant recognition for their roles in the Prom & Safety Graduation Awareness Events and Young Adult Survey data analyzing. |
| Sticker Shock Activities |
| No discussion took place. |
| TIPS For The Tool Box |
| A review and discussion took place as to where this informational series should be distributed besides the school districts. The group indicated that they should be in libraries, communitiy centers, hospitals, physician offices, youth centers, parent resource centers and also should be give to the prevention educators and counselors to utilize upon completion of a Teen Intervene, etc. where appropriate. Action Item: Colleen Banik will provide Susan Hooker with 50 packets for distribution in the Hornell and Canisteo areas. Action Item: Jim Bassage will deliver packets to Susan Hooker. |
| Table Tent Displays |
| Jim Bassage reported that the Table Tent are in Kyle King’s possession for printing. An error was identified. Action Item: Colleen Banik will contact Kyle King to see if printing has begun and if not, a correction on the identified error will be made. |
| Adult Perception Survey |
| Jim Bassage reported that the Adult Perception Survey with Task Force changes has been sent to Hillary Anderson for inputting into Survey Monkey and distribution will take place the week of July 29th. A limited amount of paper copies will be made available as well. A discussion was held to distribute the APS to corporations such as Alstom, Corning, Inc., the Department of Labor, Hospitals and the County Office Building. Action Item: Hillary Anderson will forward Survey Monkey Link to Colleen Banik for distrubiton. Action Item: Jim Bassage will provide Susan Hooker with a Survey Flyer to be sent home with youth center children for parents. Action Item: Jim Bassage will prepare and distribute Survey Flyers with tear off links. |
| Other Items: |
| No further items of discussion took place. |
| Next Meeting: |
| Next meeting to be held on September 11, 2019 at 11:00 – 1:00 p.m. at Steuben County Sheriff’s Office Bath, NY. |

| Action Items |
| --- |
| Status | Task | Start Date | Target Date | Responsible |
|  | Circulation of Adult Perception Survey | July 2019 | August 2019 | Coalition |
|  | 2019 Sticker Shock Activities | January 2019 | December 2019 | Task Force |
|  | Alcohol poster Contest/Celebrations | April 2019 | June 2019 | Jim Bassage |
|  | Sticker Shock Activities | January 2019 | September 2019 | Task Force |
|  | Adult Perception Survey Link to be forwarded to Colleen Banik for circulation | July 2019 | July 2019 | Hillary Anderson |
|  | Planning for 2019 UAD Town Hall Meeting | Summer 2019 | Fall 2019 | Task Force |
|  | Circulation of TIPS For the Tool Box | Spring 2019 | June 2019 |  |
|  | Creation of Table Tents/Post Cards | Spring 2019 | Summer 2019 | Susan Hooker and Kyle King |
|  | Nomination/Selection of Co-Chair | November 2018 | Spring 2019 | Jim Bassage |
|  | Environmental Scans in Hornell | Spring 2019 | June 2019 | Susan Hooker |

= Complete               = Pending              = Overdue